SIMATS ENGINEERING (SAVEETHA SCHOOL OF ENGINEERING)

Department of Computer Science and Engineering

CO1 ASSESSMENT TOOL 2–   Agile Sprint Planning & User Story Workshop

| Course Code: | CSA10 / CSA1004 | Course Title: | Software Engineering |
| --- | --- | --- | --- |
| CO Assessed: | CO2 | Assessment: | Assessment Tool 2 – Agile Sprint planning and user story workshop |
| Weightage: | 20% | Total Marks: | 25 |
| Co2 Statement: | Apply advanced methodologies and agile project management techniques to manage software projects effectively |  |  |
| Student Name: | Bochu Rama Krishna | Reg. No.: | 192311277 |
| Date: | 15/10/2026 | Duration: | 60 minutes |

Code of Conduct I Bochu Rama Krishna (192311277) (Name / Reg No) certify that this submission is my original work and that I have adhered to the guidelines specified for this assessment. I understand that any violation of academic integrity rules will result in disciplinary action. Signature of the Student: Rama Krishna

# Agile Sprint Planning and User Story Workshop

Project: AI-Based Student Academic Early Warning System (SAEWS) Methodology: Scrum | Sprint length: 2 weeks | Team assumption: 4 developers, 1 Scrum Master, 1 Product Owner

## 1. Project Vision and Stakeholders

### 1.1 Problem context

Institutions hold large volumes of attendance, internal assessment, assignment and examination data, but weak students are usually noticed only after a failed test or a shortage of attendance. Manual analysis is slow, inconsistent and rarely leads to a recorded follow-up.

### 1.2 Vision statement

For faculty, mentors and administrators who need to catch struggling students before it is too late, SAEWS is an AI-based academic early warning platform that integrates academic data, identifies at-risk students, raises personalized alerts and recommends interventions. Unlike manual spreadsheet tracking, SAEWS is continuous, explainable and tied to a mentoring record, so every flagged student gets a documented follow-up.

### 1.3 Project objectives (measurable)

| # | Objective | Success measure |
| --- | --- | --- |
| O1 | Collect and integrate academic data | Attendance, marks and assignment data for a class imported in under 5 minutes with validation |
| O2 | Monitor attendance and assessment performance | Per-student and per-course trends visible within 2 clicks |
| O3 | Identify students at academic risk | At-risk recall of at least 80% on historical test data; each flag shows its reasons |
| O4 | Generate personalized alerts | Alert generated within 24 hours of a risk-level change |
| O5 | Provide intervention recommendations | Every Amber/Red student receives at least one recommended action |
| O6 | Maintain mentoring records | 100% of alerts can be linked to a mentoring entry and follow-up date |
| O7 | Generate performance reports | Student and class PDF report generated in under 10 seconds |
| O8 | Provide dashboards | Role-based dashboards for faculty, mentors and admin |

### 1.4 Stakeholders

| Stakeholder | Role | Interest / what they need | Influence |
| --- | --- | --- | --- |
| Faculty / course instructor | Primary user | Class-level risk view, alerts for their course, intervention suggestions | High |
| Mentor / class advisor | Primary user | Mentee list, alert history, mentoring log, follow-up reminders | High |
| Head of Department (HoD) | Decision maker | Department risk trends, failure-rate reduction, intervention effectiveness | High |
| Academic administrator / Dean | Sponsor | Institution-wide analytics, data-driven decisions, accreditation evidence | High |
| Students | Beneficiary / secondary user | Timely, supportive feedback; own performance report | Medium |
| Parents / guardians | Indirect beneficiary | Communication on attendance and progress (where policy permits) | Low |
| Student counselor / support cell | Secondary user | Referrals of high-risk students with context | Medium |
| Examination / records office | Data provider | Accurate marks import, no duplicate entry | Medium |
| IT / system administrator | Operator | Deployment, backup, user access, integrations with LMS | Medium |
| Data protection / compliance officer | Governor | Privacy, consent, role-based access, audit trail | Medium |
| Product Owner | Scrum role | Backlog ownership, priorities, acceptance | High |
| Scrum Master and Development Team | Scrum roles | Delivery, quality, process | High |

### 1.5 Key personas

- Prof. Meera (Faculty): teaches 120 students across 2 sections; wants to know who needs help this week without opening five spreadsheets.

- Mr. Arjun (Mentor): mentors 25 students; needs a record of what was discussed and what was agreed.

- Dr. Rao (HoD): needs to know whether interventions are working.

## 2. Epics and User Stories

### 2.1 Epics

| ID | Epic | Objective covered |
| --- | --- | --- |
| E1 | Data Integration and Management | O1 |
| E2 | User Access and Security | Cross-cutting |
| E3 | Performance Monitoring | O2 |
| E4 | Risk Identification Engine (rule-based and AI) | O3 |
| E5 | Alerts and Notifications | O4 |
| E6 | Intervention Recommendations | O5 |
| E7 | Mentoring Records | O6 |
| E8 | Reports and Dashboards | O7, O8 |

### 2.2 User stories

Format: As a <user>, I want <feature>, so that <benefit>.

E1: Data Integration and Management

- US-01 As an academic administrator, I want to upload attendance, internal marks and assignment data as CSV/Excel files, so that student records are available in one place without manual re-entry.

- US-02 As an academic administrator, I want the system to validate uploaded data and show row-level errors, so that incorrect or duplicate records do not corrupt risk analysis.

- US-03 As an IT administrator, I want to connect the LMS to import learning activity (logins, time spent, resources viewed), so that engagement can be considered in risk analysis.

E2: User Access and Security

- US-04 As a user (faculty, mentor, admin), I want to log in with role-based access, so that I see only the data I am authorized to view.

- US-05 As a compliance officer, I want an audit log of who viewed or changed student data, so that privacy requirements are met.

E3: Performance Monitoring

- US-06 As a faculty member, I want to view attendance percentage per student and per course, so that I can spot low attendance early.

- US-07 As a faculty member, I want to view assessment scores and score trends across tests, so that I can see who is declining.

- US-08 As a faculty member, I want to see assignment submission status (on time, late, missed), so that I can identify disengaged students.

E4: Risk Identification Engine

- US-09 As a faculty member, I want students automatically flagged Green/Amber/Red using configurable rules (for example attendance below 75%), so that I get a transparent baseline risk view.

- US-10 As a mentor, I want an AI model to predict each student's likelihood of failing a course, so that students at risk are found before rules alone would catch them.

- US-11 As a faculty member, I want to see the top factors behind each student's risk score, so that I can trust and act on the flag.

- US-12 As an HoD, I want to configure risk thresholds, so that the system matches departmental policy.

E5: Alerts and Notifications

- US-13 As a mentor, I want an in-app alert when a mentee's risk level rises, so that I can act quickly.

- US-14 As a faculty member, I want personalized email alerts that name the student, the triggering factors and the course, so that I do not have to search for the cause.

- US-15 As a student, I want a supportive notification about my attendance or marks, so that I can correct course early.

E6: Intervention Recommendations

- US-16 As a mentor, I want suggested interventions matched to each student's risk factors (for example remedial class, peer tutoring, counseling), so that I can choose appropriate support quickly.

- US-17 As a faculty member, I want to accept, modify or reject a recommended intervention and record it, so that actions are tracked.

E7: Mentoring Records

- US-18 As a mentor, I want to log mentoring sessions with notes, action items and follow-up dates, so that there is a complete history for each mentee.

- US-19 As a mentor, I want reminders for pending follow-ups, so that no student is forgotten.

- US-20 As an HoD, I want to see whether students improved after interventions, so that I can judge mentoring effectiveness.

E8: Reports and Dashboards

- US-21 As a faculty member, I want a class dashboard showing the at-risk list and risk distribution, so that I can plan my support for the week.

- US-22 As a mentor, I want a mentee dashboard with attendance, marks, alerts and session history, so that I am prepared for each meeting.

- US-23 As an administrator, I want a department-wide dashboard of risk distribution and failure-rate trends, so that I can make data-driven decisions.

- US-24 As a faculty member, I want to generate a student performance report as PDF, so that I can share progress with the student or parents.

## 3. Acceptance Criteria (Sprint 1 stories, Given-When-Then)

Sprint 1 stories are US-01, US-02, US-04, US-06, US-07, US-09 and US-21. Criteria for the remaining backlog stories will be written during backlog refinement before the sprint in which they are selected.

### US-01: Upload academic data

- AC1: Given I am logged in as an administrator, when I upload a CSV/XLSX file in the defined template (student ID, course, date/test, value), then the data is stored and a summary shows the number of records imported.

- AC2: Given a file of up to 5,000 rows, when I upload it, then processing completes in under 60 seconds.

- AC3: Given I upload a file in the wrong format or with missing required columns, when I submit it, then nothing is saved and a message lists the missing columns.

### US-02: Validate uploaded data

- AC1: Given a file contains a row with an invalid value (attendance outside 0-100%, marks above maximum, unknown student ID), when the file is validated, then that row is rejected and listed with row number and reason.

- AC2: Given a file contains duplicate records for the same student, course and date, when it is validated, then only one record is kept and the duplicate is reported.

- AC3: Given a file has both valid and invalid rows, when I confirm the import, then valid rows are saved and I can download an error report for the rest.

### US-04: Role-based login

- AC1: Given valid credentials, when I log in, then I am taken to the dashboard for my role (faculty, mentor, admin).

- AC2: Given invalid credentials, when I log in, then access is denied with a generic error and the attempt is recorded; after 5 failed attempts the account is locked for 15 minutes.

- AC3: Given I am a faculty member, when I try to open an admin page by URL, then access is denied (HTTP 403).

- AC4: Given I am a faculty member, when I view students, then I see only students enrolled in my courses.

### US-06: Attendance monitoring

- AC1: Given attendance data is imported, when I open a course, then each student's attendance percentage is displayed, calculated as classes attended divided by classes held.

- AC2: Given a student's attendance is below the configured threshold (default 75%), when I view the list, then that student is highlighted.

- AC3: Given I select a student, when the detail page opens, then a weekly attendance trend chart is shown.

- AC4: Given the list has up to 200 students, when I open it, then it loads in under 3 seconds.

### US-07: Assessment performance and trends

- AC1: Given internal test marks are imported, when I open a student's profile, then scores for all tests are listed with percentage and class average.

- AC2: Given a student scored lower in each of the last two consecutive tests, when I view the profile, then a "declining trend" indicator is displayed.

- AC3: Given I filter by course and test, when I apply the filter, then the list and chart update without a full page reload.

### US-09: Rule-based risk flagging

- AC1: Given attendance, marks and assignment data exist, when the risk job runs (manually or on its weekly schedule), then every student receives a risk level of Green, Amber or Red.

- AC2: Given attendance is below 65%, or average internal marks are below 40%, or there are 3 or more missed assignments, when the job runs, then the student is flagged Red.

- AC3: Given a student meets exactly one Amber condition (attendance 65-74%, marks 40-50%, or 1-2 missed assignments), when the job runs, then the student is flagged Amber.

- AC4: Given a student is flagged, when I open the flag, then the exact rules that triggered it are listed.

- AC5: Given the risk job is run twice with unchanged data, when it finishes, then results are identical and no duplicate records are created.

### US-21: Faculty class dashboard

- AC1: Given I am faculty and select a course, when the dashboard loads, then it shows total students, counts per risk level, and a list of Amber/Red students sorted by risk.

- AC2: Given I click a student in the at-risk list, when the page opens, then I see that student's attendance, marks and flag reasons.

- AC3: Given no data has been imported for the course, when the dashboard loads, then a clear "no data yet" message is shown instead of an error.

- AC4: Given the dashboard is opened on a laptop or tablet, when it renders, then all elements are readable without horizontal scrolling.

## 4. Prioritized Product Backlog

### 4.1 Prioritization approach

Stories are ranked using MoSCoW categories combined with business value (1-10), dependency order, and risk (technical uncertainty). Foundation items that unblock others (data, login) rank high even when their direct value is moderate.

### 4.2 Ordered backlog

| Rank | ID | Story (short) | MoSCoW | Value | Dependency | Reason for position |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | US-04 | Role-based login | Must | 8 | None | Required before any user data is shown |
| 2 | US-01 | Upload academic data | Must | 10 | US-04 | Without data there is no system |
| 3 | US-02 | Validate data | Must | 9 | US-01 | Bad data makes risk output unreliable |
| 4 | US-06 | Attendance monitoring | Must | 9 | US-01 | Core monitoring objective |
| 5 | US-07 | Assessment trends | Must | 9 | US-01 | Core monitoring objective |
| 6 | US-09 | Rule-based risk flags | Must | 10 | US-06, US-07 | Delivers the core early-warning value |
| 7 | US-21 | Faculty class dashboard | Must | 9 | US-09 | Makes risk visible to the main user |
| 8 | US-08 | Assignment status | Must | 7 | US-01 | Third input to risk rules |
| 9 | US-11 | Risk explanation | Must | 8 | US-09 | Trust and actionability |
| 10 | US-13 | In-app alerts | Must | 8 | US-09 | Turns flags into action |
| 11 | US-16 | Intervention suggestions | Must | 9 | US-09 | Core objective O5 |
| 12 | US-18 | Log mentoring sessions | Must | 8 | US-04 | Core objective O6 |
| 13 | US-22 | Mentor dashboard | Should | 7 | US-13, US-18 | Supports mentor workflow |
| 14 | US-14 | Email alerts | Should | 7 | US-13 | Reaches users outside the app |
| 15 | US-17 | Accept/reject interventions | Should | 6 | US-16 | Tracks actions taken |
| 16 | US-19 | Follow-up reminders | Should | 6 | US-18 | Prevents missed follow-ups |
| 17 | US-12 | Configurable thresholds | Should | 6 | US-09 | Policy flexibility |
| 18 | US-24 | PDF student report | Should | 6 | US-06, US-07 | Required output, not blocking |
| 19 | US-10 | AI/ML risk prediction | Should | 9 | US-09 and history | High value, but needs labeled data and tuning; built on a working rule baseline |
| 20 | US-23 | Admin dashboard | Should | 7 | US-09, US-20 | Needs accumulated data |
| 21 | US-20 | Intervention effectiveness | Should | 7 | US-17, US-18 | Needs history |
| 22 | US-03 | LMS integration | Could | 6 | US-01 | Depends on LMS API access |
| 23 | US-15 | Student notifications | Could | 5 | US-13 | Needs careful wording and policy approval |
| 24 | US-05 | Audit log | Could | 5 | US-04 | Important for compliance, can follow core features |

### 4.3 Release plan (indicative)

| Sprint | Theme |
| --- | --- |
| Sprint 1 | Data, access and rule-based risk visibility (Walking skeleton) |
| Sprint 2 | Assignments, explanations, alerts, interventions, mentoring log |
| Sprint 3 | Mentor dashboard, email alerts, reminders, thresholds, PDF reports |
| Sprint 4 | AI model with explanations, admin dashboard, effectiveness tracking |
| Sprint 5 | LMS integration, student notifications, audit log, hardening, UAT |

## 5. Sprint 1 Backlog and Task Breakdown

Capacity: 4 developers x 8 working days x about 5 productive hours = roughly 160 hours. Planned effort is about 135-145 hours, leaving a buffer for meetings, reviews and defects. Assumed velocity for a new team: about 34 story points.

| Story | Points | Task | Est. hours |
| --- | --- | --- | --- |
| US-04 Role-based login | 5 | Design User/Role tables | 3 |
|  |  | Implement login, password hashing, session/JWT | 8 |
|  |  | Implement role-based route guards and course-level data scoping | 6 |
|  |  | Build login UI and role-based landing redirect | 4 |
|  |  | Unit and security tests (lockout, 403) | 4 |
| US-01 Upload academic data | 5 | Define CSV/XLSX templates for attendance, marks, assignments | 3 |
|  |  | Design Student, Course, Enrollment, Attendance, Assessment tables | 5 |
|  |  | Build upload endpoint and file parser | 8 |
|  |  | Build upload UI with import summary | 5 |
|  |  | Integration test with 5,000-row sample | 3 |
| US-02 Validate data | 3 | Implement validation rules (ranges, unknown IDs, missing columns) | 6 |
|  |  | Duplicate detection | 3 |
|  |  | Row-level error report (on screen and downloadable) | 4 |
|  |  | Tests with invalid sample files | 3 |
| US-06 Attendance monitoring | 5 | Attendance percentage query/service | 4 |
|  |  | Course attendance table UI with threshold highlight | 6 |
|  |  | Student attendance trend chart | 5 |
|  |  | Performance check for 200 students | 2 |
| US-07 Assessment trends | 3 | Marks and class-average query | 3 |
|  |  | Student profile marks view | 5 |
|  |  | Declining-trend logic (two consecutive drops) | 3 |
|  |  | Tests | 2 |
| US-09 Rule-based risk flags | 8 | Define rules and thresholds in config file | 3 |
|  |  | Build risk calculation service (attendance, marks, missed assignments) | 10 |
|  |  | RiskScore table and idempotent storage | 4 |
|  |  | Weekly scheduler plus manual trigger | 4 |
|  |  | Store triggered-rule reasons | 3 |
|  |  | Unit tests for each rule and boundary values | 6 |
| US-21 Faculty class dashboard | 5 | Dashboard API (counts, at-risk list) | 5 |
|  |  | Dashboard UI with risk summary cards and sorted list | 8 |
|  |  | Student detail drill-down | 4 |
|  |  | Empty-state handling and responsive layout | 3 |
| Total | 34 |  | about 140 |

Notes: Assignment-based rules in US-09 use the missed assignments count from the marks/assignments upload template. The dedicated assignment view (US-08) is planned for Sprint 2.

## 6. Effort Estimation Using Story Points

### 6.1 Technique

The team uses Planning Poker with the modified Fibonacci sequence (1, 2, 3, 5, 8, 13). Estimates are relative to a reference story: US-07 (assessment trends, three well-understood read operations plus a simple calculation) is fixed at 3 points. Each team member votes privately; differences of more than one card trigger discussion of assumptions, then re-vote until the team converges. Story points reflect effort, complexity and uncertainty, not hours.

### 6.2 Estimates and justification

| Story | Points | Justification |
| --- | --- | --- |
| US-04 Role-based login | 5 | Well-known pattern, but includes security hardening (lockout, 403) and course-level data scoping that touches every later feature. |
| US-01 Upload data | 5 | Several data models plus file parsing and UI; moderate uncertainty over messy real-world files. |
| US-02 Validate data | 3 | Rules are simple and clear; builds on US-01 parser; mostly logic and reporting. |
| US-06 Attendance monitoring | 5 | Calculation is easy, but needs both a table and a trend chart plus a performance target. |
| US-07 Assessment trends | 3 | Reference story: straightforward queries, one simple trend rule, one view. |
| US-09 Rule-based risk flags | 8 | Highest complexity and importance: multiple data sources, boundary conditions, scheduling, idempotency and explanation storage. Split further if it grows beyond 8. |
| US-21 Faculty dashboard | 5 | Several UI components and an API; depends on risk data but logic is modest. |
| Total | 34 | Matches assumed velocity; no story exceeds 8 points, so none needs splitting. |

### 6.3 Why these estimates are realistic

- The largest story (8) is only 24% of the sprint, so one overrun does not break the goal.

- Roughly 140 of 160 available hours are planned, which leaves a buffer for defects and reviews.

- Velocity will be measured at the end of Sprint 1 and used to adjust Sprint 2 planning.

## 7. Sprint Goal, Deliverables and Definition of Done

### 7.1 Sprint 1 goal

"By the end of Sprint 1, an authenticated faculty member can upload and validate attendance and marks data for a course and view a rule-based Green/Amber/Red risk list with the reasons behind each flag, so that the team has a working end-to-end early-warning slice to demonstrate and refine."

### 7.2 Expected deliverables (increment)

- Working login with admin, faculty and mentor roles.

- Data upload (CSV/XLSX) with validation and a downloadable error report.

- Database schema for students, courses, enrollments, attendance, assessments and risk scores.

- Attendance and assessment views with trend indicators.

- Rule-based risk engine with configurable rules file, weekly job and manual trigger.

- Faculty class dashboard with risk summary and at-risk student list.

- Automated tests for validation and risk rules; deployment on a shared test environment.

- Sample dataset and short user guide for the Sprint Review demo.

### 7.3 Definition of Done

- Code reviewed by at least one other developer and merged to the main branch.

- Unit tests written and passing; all acceptance criteria verified.

- No open critical or high-severity defects.

- Deployed to the test environment and demonstrated to the Product Owner.

- Documentation (API notes and user steps) updated.

### 7.4 Sprint ceremonies

| Ceremony | When | Purpose |
| --- | --- | --- |
| Sprint Planning | Day 1 | Confirm goal, stories, tasks |
| Daily Scrum | Daily, 15 min | Progress, impediments |
| Backlog refinement | Mid-sprint | Prepare Sprint 2 stories and acceptance criteria |
| Sprint Review | Last day | Demo to stakeholders (faculty and mentor representatives) |
| Retrospective | Last day | Improve the process |

### 7.5 Risks and mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Real data not available early | Delays testing | Use a synthetic dataset matching the upload templates |
| Messy or inconsistent file formats | Validation rework | Fix templates with the Product Owner; show clear error messages |
| US-09 rules disputed by faculty | Rework | Keep rules in a config file; confirm thresholds at the Sprint Review |
| Privacy concerns about student data | Blocked rollout | Role-based access from Sprint 1; no protected attributes used in risk rules |
| Team new to the stack | Velocity lower than planned | Conservative 34-point commitment; pair on US-09 |

### 7.6 Sprint 1 Review demo flow

- Log in as admin and upload a valid file, then an invalid one to show errors.

- Log in as faculty and open the course attendance and marks views.

- Run the risk job and open the dashboard.

- Click a Red student to show the triggered rules.

- Collect stakeholder feedback to refine Sprint 2 backlog items.